## P14_Budget
EnRLD 2025 Reforestation Activities Budget - FMU P14 ONLY |  |  |  |  | Reforestation Workplan Schedule
[5 empty] | Fall 2024 | Winter 2025 | Spring 2025 | Summer 2025 | Fall 2025 | Winter 2026 | Spring 2026
Proposed Activity | Units | No. of Units | Unit Cost | Total | Oct - Dec | Jan - Mar | Apr - May | Jun - Aug | Sept - Dec | Jan - Mar | Apr - Jun
Phase 1 - Preparation (planning, review shapefiles, block layout, admin, etc.) |  |  |  |  | Preparation
Project Management1 | hours | 300 | 300 | 90000
Project / Planning Silviculture Forester2 | hours | 75 | 300 | 22500
Staffing3,4 (if required) | hours | 35 | 150 | 5250
GIS tasks - spatial data mgmt & mapping | hours | 250 | 250 | 62500
Sub-contractor5 (describe) | - | 0 | 0 | 0
Misc.6 (describe) | - | 0 | 0 | 0
Subtotal - Preparation |  |  |  | 180250
Project Hectares |  |  |  | 960
Proposed Phase Cost/Hectare |  |  |  | 187.7604
Phase 2 - Mechanical Site Preparation |  |  |  |  | Mechanical Site Preparation
Project Management1 | hours | 300 | 300 | 90000
Project / Planning Silviculture Forester2 | hours | 80 | 300 | 24000
Staffing3,4 (if required) | hours | 100 | 150 | 15000
GIS tasks - spatial data mgmt & mapping | hours | 35 | 250 | 8750
Buncher | $ / ha | 960 | 1850 | 1776000
Pile Burning & Scanning | days | 1 | 1200 | 1200
Sub-contractor5 (describe) | - | 0 | 0 | 0
Misc.6 (describe) | - | 0 | 0 | 0
Accomodation (incl. sustenance)7 | man hours | 50 | 250 | 12500
Vehicle (incl. mileage) | days | 10 | 225 | 2250
Subtotal - Mechanical Site Preparation |  |  |  | 1929700
Project Hectares |  |  |  | 960
Proposed Phase Cost/Hectare |  |  |  | 2010.1042
Phase 3 - Chemical Site Preparation | [6 empty] | Chemical Site Preparation
Project Management1 | hours | 50 | 300 | 15000
Project / Planning Silviculture Forester2 | hours | 35 | 300 | 10500
Staffing3,4 (if required) | hours | 20 | 150 | 3000
GIS tasks - spatial data mgmt & mapping | hours | 20 | 250 | 5000
Chemical Site Prep | $ / ha | 960 | 350 | 336000
Off-Target Application Assessment | days | 1 | 2500 | 2500
Sub-contractor5 (describe) | - | 0 | 0 | 0
Misc.6 (describe) | - | 0 | 0 | 0
Accomodation (incl. sustenance)7 | man hours | 20 | 250 | 5000
Vehicle (incl. mileage) | days | 5 | 225 | 1125
Helicopter8 (if required) | hours | 40 | 900 | 36000
Subtotal - Chemical Site Preparation |  |  |  | 414125
Project Hectares |  |  |  | 960
Proposed Phase Cost/Hectare |  |  |  | 431.3802
Phase 4 - Planting | [6 empty] | Planting
Project Management1 | hours | 75 | 300 | 22500
Project / Planning Silviculture Forester2 | hours | 35 | 300 | 10500
Staffing3,4 (if required) | hours | 40 | 650 | 26000
GIS tasks - spatial data mgmt & mapping | hours | 20 | 250 | 5000
Planting Activities | # seedlings | 1137500 | 0.4 | 455000
Nursery Costs (incl. transport) | # seedlings | 1137500 | 0.4 | 455000 | Order Seedlings
Sub-contractor5 (describe) | - | 0 | 0 | 0
Misc.6 (describe) | - | 0 | 0 | 0
Accomodation (incl. sustenance)7 | man hours | 16 | 250 | 4000
Vehicle (inc. mileage) | days | 5 | 225 | 1125
Helicopter8 (if required) | hours | 40 | 900 | 36000
Subtotal - Planting |  |  |  | 1015125
Project Hectares |  |  |  | 960
Proposed Phase Cost/Hectare |  |  |  | 1057.4219
Office Compilation | [8 empty] | Office Compilation
Project Management1 | hours | 12 | 300 | 3600
Staffing3 (if required) | hours | 20 | 150 | 3000
GIS tasks - spatial data mgmt & mapping | hours | 8 | 250 | 2000
Subtotal - Office Compilation |  |  |  | 8600 | [5 empty] | Final Reporting
Final Reporting
Project Management1 | hours | 8 | 300 | 2400
Staffing3 (if required) | hours | 12 | 150 | 1800
GIS tasks - spatial data mgmt & mapping | hours | 10 | 250 | 2500
Subtotal - Final Reporting |  |  |  | 6700
Proposed Project Total |  |  |  | 3554500
Project Hectares9 |  |  |  | 960
Proposed Project Cost/Hectare10 |  |  |  | 3702.6042
Note: All text in red is sample information for illustration purposes only and should be replaced with information that is relevant to the applicant. All rates provided are considered to be examples and may not be reflective of current market value, nor should they be taken as guidelines or absolutes.
Assumptions:
1 - Registered Professional Practitioner - office rate at 8 hrs/day (average)
2 - Registered Professional Practitioner - field rate at 10 hrs/day (average) and includes… (eg. field equipment, truck, etc.)
3 - Intermediate / Junior Professional - office rate at 8 hrs/day (average)
4 - Intermediate / Junior Professional - field rate at 10 hrs/day (average) and includes… (eg. field equipment, truck, etc.)
5 - Describe sub-contracted work (if applicable)
6 - Describe miscellaneous items (if applicable)
7 - Accomodation and sustenance can be per diem, at cost with reciepts, or reasonable average rates
8 - "Dry" (no fuel/oil) or "Wet" (fuel/oil included) rate, etc.
9 - Estimated total project hectares (depending on area/scope)
10 - Proposals will be evaluated on a cost per hectare basis

## P20_Budget
EnRLD 2025 Reforestation Activities Budget - FMU P20 ONLY |  |  |  |  | Reforestation Workplan Schedule
[5 empty] | Fall 2024 | Winter 2025 | Spring 2025 | Summer 2025 | Fall 2025 | Winter 2026 | Spring 2026
Proposed Activity | Units | No. of Units | Unit Cost | Total | Oct - Dec | Jan - Mar | Apr - May | Jun - Aug | Sept - Dec | Jan - Mar | Apr - Jun
Phase 1 - Preparation (planning, review shapefiles, block layout, admin, etc.) |  |  |  |  | Preparation
Project Management1 | hours | 250 | 300 | 75000
Project / Planning Silviculture Forester2 | hours | 50 | 300 | 15000
Staffing3,4 (if required) | hours | 35 | 150 | 5250
GIS tasks - spatial data mgmt & mapping | hours | 150 | 250 | 37500
Sub-contractor5 (describe) | - | 0 | 0 | 0
Misc.6 (describe) | - | 0 | 0 | 0
Subtotal - Preparation |  |  |  | 132750
Project Hectares |  |  |  | 512
Proposed Phase Cost/Hectare |  |  |  | 259.2773
Phase 2 - Mechanical Site Preparation |  |  |  |  | Mechanical Site Preparation
Project Management1 | hours | 250 | 300 | 75000
Project / Planning Silviculture Forester2 | hours | 80 | 300 | 24000
Staffing3,4 (if required) | hours | 100 | 150 | 15000
GIS tasks - spatial data mgmt & mapping | hours | 35 | 250 | 8750
Buncher | $ / ha | 512 | 1850 | 947200
Pile Burning & Scanning | days | 1 | 1200 | 1200
Sub-contractor5 (describe) | - | 0 | 0 | 0
Misc.6 (describe) | - | 0 | 0 | 0
Accomodation (incl. sustenance)7 | man hours | 50 | 250 | 12500
Vehicle (incl. mileage) | days | 10 | 225 | 2250
Subtotal - Mechanical Site Preparation |  |  |  | 1085900
Project Hectares |  |  |  | 512
Proposed Phase Cost/Hectare |  |  |  | 2120.8984
Phase 3 - Chemical Site Preparation | [6 empty] | Chemical Site Preparation
Project Management1 | hours | 50 | 300 | 15000
Project / Planning Silviculture Forester2 | hours | 35 | 300 | 10500
Staffing3,4 (if required) | hours | 20 | 150 | 3000
GIS tasks - spatial data mgmt & mapping | hours | 20 | 250 | 5000
Chemical Site Prep | $ / ha | 512 | 350 | 179200
Off-Target Application Assessment | days | 1 | 2500 | 2500
Sub-contractor5 (describe) | - | 0 | 0 | 0
Misc.6 (describe) | - | 0 | 0 | 0
Accomodation (incl. sustenance)7 | man hours | 20 | 250 | 5000
Vehicle (incl. mileage) | days | 5 | 225 | 1125
Helicopter8 (if required) | hours | 40 | 900 | 36000
Subtotal - Chemical Site Preparation |  |  |  | 257325
Project Hectares |  |  |  | 512
Proposed Phase Cost/Hectare |  |  |  | 502.5879
Phase 4 - Planting | [6 empty] | Planting
Project Management1 | hours | 50 | 300 | 15000
Project / Planning Silviculture Forester2 | hours | 35 | 300 | 10500
Staffing3,4 (if required) | hours | 40 | 650 | 26000
GIS tasks - spatial data mgmt & mapping | hours | 20 | 250 | 5000
Planting Activities | # seedlings | 500000 | 0.4 | 200000
Nursery Costs (incl. transport) | # seedlings | 500000 | 0.4 | 200000 | Order Seedlings
Sub-contractor5 (describe) | - | 0 | 0 | 0
Misc.6 (describe) | - | 0 | 0 | 0
Accomodation (incl. sustenance)7 | man hours | 16 | 250 | 4000
Vehicle (inc. mileage) | days | 5 | 225 | 1125
Helicopter8 (if required) | hours | 40 | 900 | 36000
Subtotal - Planting |  |  |  | 497625
Project Hectares |  |  |  | 512
Proposed Phase Cost/Hectare |  |  |  | 971.9238
Office Compilation | [8 empty] | Office Compilation
Project Management1 | hours | 12 | 300 | 3600
Staffing3 (if required) | hours | 20 | 150 | 3000
GIS tasks - spatial data mgmt & mapping | hours | 8 | 250 | 2000
Subtotal - Office Compilation |  |  |  | 8600 | [5 empty] | Final Reporting
Final Reporting
Project Management1 | hours | 8 | 300 | 2400
Staffing3 (if required) | hours | 12 | 150 | 1800
GIS tasks - spatial data mgmt & mapping | hours | 10 | 250 | 2500
Subtotal - Final Reporting |  |  |  | 6700
Proposed Project Total |  |  |  | 1988900
Project Hectares9 |  |  |  | 512
Proposed Project Cost/Hectare10 |  |  |  | 3884.5703
Note: All text in red is sample information for illustration purposes only and should be replaced with information that is relevant to the applicant. All rates provided are considered to be examples and may not be reflective of current market value, nor should they be taken as guidelines or absolutes.
Assumptions:
1 - Registered Professional Practitioner - office rate at 8 hrs/day (average)
2 - Registered Professional Practitioner - field rate at 10 hrs/day (average) and includes… (eg. field equipment, truck, etc.)
3 - Intermediate / Junior Professional - office rate at 8 hrs/day (average)
4 - Intermediate / Junior Professional - field rate at 10 hrs/day (average) and includes… (eg. field equipment, truck, etc.)
5 - Describe sub-contracted work (if applicable)
6 - Describe miscellaneous items (if applicable)
7 - Accomodation and sustenance can be per diem, at cost with reciepts, or reasonable average rates
8 - "Dry" (no fuel/oil) or "Wet" (fuel/oil included) rate, etc.
9 - Estimated total project hectares (depending on area/scope)
10 - Proposals will be evaluated on a cost per hectare basis

## P14 and P20_Combined
EnRLD 2025 Reforestation Activities Budget (P14 and P20) |  |  |  |  | Reforestation Workplan Schedule
[5 empty] | Fall 2024 | Winter 2025 | Spring 2025 | Summer 2025 | Fall 2025 | Winter 2026 | Spring 2026
Proposed Activity | Units | No. of Units | Unit Cost | Total | Oct - Dec | Jan - Mar | Apr - May | Jun - Aug | Sept - Dec | Jan - Mar | Apr - Jun
Phase 1 - Preparation (planning, review shapefiles, block layout, admin, etc.) |  |  |  |  | Preparation
Project Management1 | hours | 500 | 300 | 150000
Project / Planning Silviculture Forester2 | hours | 75 | 300 | 22500
Staffing3,4 (if required) | hours | 35 | 150 | 5250
GIS tasks - spatial data mgmt & mapping | hours | 250 | 250 | 62500
Sub-contractor5 (describe) | - | 0 | 0 | 0
Misc.6 (describe) | - | 0 | 0 | 0
Subtotal - Preparation |  |  |  | 240250
Project Hectares |  |  |  | 1200
Proposed Phase Cost/Hectare |  |  |  | 200.2083
Phase 2 - Mechanical Site Preparation |  |  |  |  | Mechanical Site Preparation
Project Management1 | hours | 350 | 300 | 105000
Project / Planning Silviculture Forester2 | hours | 80 | 300 | 24000
Staffing3,4 (if required) | hours | 100 | 150 | 15000
GIS tasks - spatial data mgmt & mapping | hours | 35 | 250 | 8750
Buncher | $ / ha | 1200 | 1850 | 2220000
Pile Burning & Scanning | days | 2 | 1200 | 2400
Sub-contractor5 (describe) | - | 0 | 0 | 0
Misc.6 (describe) | - | 0 | 0 | 0
Accomodation (incl. sustenance)7 | man hours | 50 | 250 | 12500
Vehicle (incl. mileage) | days | 10 | 225 | 2250
Subtotal - Mechanical Site Preparation |  |  |  | 2389900
Project Hectares |  |  |  | 1200
Proposed Phase Cost/Hectare |  |  |  | 1991.5833
Phase 3 - Chemical Site Preparation | [6 empty] | Chemical Site Preparation
Project Management1 | hours | 50 | 300 | 15000
Project / Planning Silviculture Forester2 | hours | 35 | 300 | 10500
Staffing3,4 (if required) | hours | 20 | 150 | 3000
GIS tasks - spatial data mgmt & mapping | hours | 20 | 250 | 5000
Chemical Site Prep | $ / ha | 1200 | 350 | 420000
Off-Target Application Assessment | days | 1 | 2500 | 2500
Sub-contractor5 (describe) | - | 0 | 0 | 0
Misc.6 (describe) | - | 0 | 0 | 0
Accomodation (incl. sustenance)7 | man hours | 20 | 250 | 5000
Vehicle (incl. mileage) | days | 5 | 225 | 1125
Helicopter8 (if required) | hours | 40 | 900 | 36000
Subtotal - Chemical Site Preparation |  |  |  | 498125
Project Hectares |  |  |  | 1200
Proposed Phase Cost/Hectare |  |  |  | 415.1042
Phase 4 - Planting Activities | [6 empty] | Planting
Project Management1 | hours | 55 | 300 | 16500
Project / Planning Silviculture Forester2 | hours | 35 | 300 | 10500
Staffing3,4 (if required) | hours | 40 | 650 | 26000
GIS tasks - spatial data mgmt & mapping | hours | 20 | 250 | 5000
Planting Activities | # seedlings | 1750000 | 0.4 | 700000
Nursery Costs (incl. transport) | # seedlings | 1750000 | 0.4 | 700000 | Order Seedlings
Sub-contractor5 (describe) | - | 0 | 0 | 0
Misc.6 (describe) | - | 0 | 0 | 0
Accomodation (incl. sustenance)7 | man hours | 16 | 250 | 4000
Vehicle (inc. mileage) | days | 5 | 225 | 1125
Helicopter8 (if required) | hours | 40 | 900 | 36000
Subtotal - Planting |  |  |  | 1499125
Project Hectares |  |  |  | 1200
Proposed Phase Cost/Hectare |  |  |  | 1249.2708
Office Compilation | [8 empty] | Office Compilation
Project Management1 | hours | 12 | 300 | 3600
Staffing3 (if required) | hours | 20 | 150 | 3000
GIS tasks - spatial data mgmt & mapping | hours | 8 | 250 | 2000
Subtotal - Office Compilation |  |  |  | 8600 | [5 empty] | Final Reporting
Final Reporting
Project Management1 | hours | 8 | 300 | 2400
Staffing3 (if required) | hours | 12 | 150 | 1800
GIS tasks - spatial data mgmt & mapping | hours | 10 | 250 | 2500
Subtotal - Final Reporting |  |  |  | 6700
Proposed Project Total |  |  |  | 4642700
Project Hectares9 |  |  |  | 1200
Proposed Project Cost/Hectare10 |  |  |  | 3868.9167
Note: All text in red is sample information for illustration purposes only and should be replaced with information that is relevant to the applicant. All rates provided are considered to be examples and may not be reflective of current market value, nor should they be taken as guidelines or absolutes.
Assumptions:
1 - Registered Professional Practitioner - office rate at 8 hrs/day (average)
2 - Registered Professional Practitioner - field rate at 10 hrs/day (average) and includes… (eg. field equipment, truck, etc.)
3 - Intermediate / Junior Professional - office rate at 8 hrs/day (average)
4 - Intermediate / Junior Professional - field rate at 10 hrs/day (average) and includes… (eg. field equipment, truck, etc.)
5 - Describe sub-contracted work (if applicable)
6 - Describe miscellaneous items (if applicable)
7 - Accomodation and sustenance can be per diem, at cost with reciepts, or reasonable average rates
8 - "Dry" (no fuel/oil) or "Wet" (fuel/oil included) rate, etc.
9 - Estimated total project hectares (depending on area/scope)
10 - Proposals will be evaluated on a cost per hectare basis